## Sheet1
Stand-up questions | Week #1 | Week #2 | Week #3 | Week #4 | Week #5 | Week #6 | Week #7 | Week #8
| 02/10/2025-02/24/2025 | 02/25/2025-03/10/2025 | 03/11/2025-03/24/2025 | 03/25/2025-04/07/2025 | 04/08/2025-04/14/2025 | 04/15/2025-04/21/2025 | 04/22/2025-04/28/2025 | 04/29/2025-05/11/2025
Purva Bansod
What tasks did I work on / complete? | Created SQL schema (Users, Restaurants, Tables). | /register, /login, unit tests. | POST /bookings (create & email stub), DELETE /bookings/{id} cancel. | CRUD /reviews endpoints; SQL trigger to recalc average rating. | /restaurants/{id} PUT (update details) | SQL views for monthly analytics, exposed via /admin/analytics. | Prepared project for deployment | Final bug fixes
What am I planning to work on next? | Implement /register & /login with JWT; seed 25 mock restaurants. | booking business‑rules trigger & Reservations table | add review tables & endpoints skeleton. | Write stored procedure for booking conflict detection. | table‑size availability generator; reset daily counts. | city & state breakdown stats. | Test app end-to-end | Present demo
What tasks are blocked waiting on another team member? | NA | NA | NA | Waiting for delete API test | NA | NA | NA | N/A
Priyanka Angad Jadhav
What tasks did I work on / complete? | Bootstrapped FastAPI app, health‑check endpoint, Created SQL Achema | /restaurants/search endpoint with +/-30 min availability logic. | SendGrid integration for confirmation emails; ECS dev deploy. | Worked on admin api | Implemented manager api | /admin/restaurants/pending ¦ /approve ¦ /reject endpoints. | Supported integration testing | Created login walkthrough
What am I planning to work on next? | Write api for resturants | optimise search query | Worked on API | Work on manager api | handle cors issue | stress‑test bulk approve; write load test script. | Work on diagrams | Submit GitHub + documentation
What tasks are blocked waiting on another team member? | NA | NA | N/A | N/A | NA | NA | N/A | NA
Preetam Avinash Maske
What tasks did I work on / complete? | Created wireframes login / register wireframes. | hooked login / register UI to API, token stored in localStorage; route guards. | auth guard refactor; basic profile page placeholder. | Google Maps embed on restaurant detail page; responsive tweaks. | Worked on Admin UI | admin layout & pending approvals table. | Verified schema compliance and app boot, support integration | Provided DB schema ER diagram and docs
What am I planning to work on next? | Set up somebuild auth forms with React‑Hook‑Form wire to backend once JWT endpoints exist. customer and admin user interface | success / error auth states styling. | styles cleanup, loading skeletons. | Help with seed data adjustments | multi‑step wizard to add new listing (details → hours → photos). | sort & filter on approvals list; admin analytics | Create final SQL export and notes | Review grading checklist
What tasks are blocked waiting on another team member? | JWT endpoints | NA | NA | NA | NA | NA | NA | N/A
Priyanka Ajit Mutha
What tasks did I work on / complete? | Created wireframes for customer | search page layout, restaurant card component skeleton. | restaurant list with timeslot buttons; modal to confirm booking. | Review list component with lazy‑load; rating input, my bookings | Worked Reviews UI | Worked on validation of manager UI | Worked on integration | Final Bug fixes
What am I planning to work on next? | Design search page (date, time, party size, geo filters). | integrate search results, clickable timeslot buttons. | booking success screen & add to my bookings | Check review submission | Work on Manager UI for add restaurant | polish dashboard styling | Work on documents, diagrams | Finalize README and deployment note
What tasks are blocked waiting on another team member? | NA | waiting for search endpoint pagination contract | Waiting on API for user role validation | awaiting review POST endpoint test data | NA | sample analytics data export | NA | NA